## Sheet1
PROJECT: USER TESTING DIGITA SOLUTIONS FOR ADOPTION TO WOMEN-LED MICROENTERPRISES
|  | Phase 6 & 7 | Co-creation and Adaptation of Solutions Phase Tracker
|  | Duration | November 2024 - March 2025
Name of SP
Name of Product
Name of Intermediaries
To be completed together with GFA UX Consultant
| Name/Description | Description of status quo before adaptation | Description of goal (after adaptation) | Expected Impact | Expected Completion Date | Current status @ Dec 2024 | January 2025 | 2025-02-01 | March 2025 | Field Testing & Validation Phase
| Please provide a descriptive name | Please provide a short yet detailed description of the status before the adaptation | Please provide a short yet detailed description of the goal of the adaptation. Make sure to mention what specifically should be changed. | Please provide a concise description of the added value of this adaptation towards female microentrepreneurs. Why do they profit from this change? | Provide a date. | Please respond to both bullet points below: - Planned, Ongoing or Completed. - As planned or current challenge: [explanation of challenge]
Example | New One-Time-Password (OTP) Delivery Path | OTP is delivered via email. However microentrepreneurs often have connectivity issues making OTP delivery via SMS easier | SMS is added as the new default way of sending OTPs. Users using the app would be receiving an SMS instead of a Email containing their OTP | Microentrepreneurs have struggled receiving OTPs via mail because they are not used to handling emails and often do not have an email account. Also connectivity issues to the internet are circumvented using SMS OTPs. | 25th February | - Ongoing - Current challenge: SP informed us that they have a find a suitable business model for bearing the costs of the additional SMS to be send. This delays the implementation of the OTP SMS path.
1+A13:L24 | Integrate Business Growth Tools into the App | the NEST platform is used only by susu agents and micro-finance organizations for savings not addressing the use of digital tools by wemon micro-entrepreneurs. | Intergrating business growth tools on the app or creating a customer app will help women micro-entrepreneurs track their finances while saving orwithdrawing money at the comfort of their business | Women Mirco-entrepreneurs can use the appcomfortable and easily for their business transactions. T | December, 2024 | Completed
2 | Redesign Onboarding Process to Simplify Registration | the onboarding proess is quite cubersome requesting for email and digital adress as requirement to be able to move to the next phase. Other requirement is a passport picture which a difficutl to upload a photo when the internet has bad connectivity. Considering women in the informal sector, these requirements hinder their registration process making them frustrated in the end | Requirements for onbaording should include name, phone number, place of business etc to make it more simplified and easy to fill. Taking out email will make it easier to register a new client since most women do not own or know what emails are | issues of emails and passport pictures will not be a requirment to help make registering new clients will be easier and smooth |  | Ongoing
3 | Introduce Offline Functionality | the NEST mobile app relies soley on internet connectivity to function. However, there are areas which have very poor or no internet connectivity | a feature that will aid agents make transactions later be transferred when there's internet connectivty | offline functionalities will help agents register and make transactions in areas with low or no internet connectivity | 28th February, 2025 | Planned
4
5
6
7
8
9
10